## Sheet1
TEST CASE
Course Code: |  | SFT101NAA |  | Group: |  | 3
Test Date: |  | 2023-04-01 |  | Tester |  | Richard
| Test ID | AT001
Function Prototype |  | struct Map addRoute(const struct Map* map, const struct Route* route)
Assumption |  | All the other functions except for the function to test here works properly
ID | Test Type | Test Case Description | Test Data | Expected Results | Status ( Pass/ Fail) | Additional Comments
AT001 | Acceptance | Sample Output. Create an invalid destination and have the program recognize destination input is invalid | 20 .5 28x | Invalid destination | Pass
AT002 | Acceptance | Sample Output. Create an invalid size and have the program recognize size input is invalid | 20 2 12L | Invalid size | Pass
AT003 | Acceptance | Sample Output. Create an invalid weight and have the program recognize weight input is invalid | 1005 .5 12L | Invalid weight | Fail | Program displayed Invalid weight, however did not newline before input loop.
AT003.1 |  |  |  |  | Pass
AT004 | Acceptance | Sample Output. Test first destination closest to blue Truck without diversion. | 20 .5 12L | Ship on BLUE LINE, no diversion | Fail | Program immediately crashed. Exception thrown. Error pointed at line 137, structure.c
AT004.1 |  |  | 20 .5 11L | Ship on BLUE LINE, no diversion | Pass | Map was displayed incorrectly. 12L was a building that was not validated. To properly test BLUE route changed destination to 11L.
AT005 | Acceptance | Sample Output. Test first destination closest to Green Truck with diversion. | 200 1.0 8Y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y, 8Y | Fail | Program immediately crashed. Exception thrown. Error pointed at line 203, mapping.c
AT005.1 |  |  | 200 1.0 7Y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y | Fail | Map was displayed incorrectly. 8Y was a building that was not validated. To properly test GREEEN route changed destination to 7Y. Program is incorrectly validating 7Y to be a building.
AT005.2 |  |  |  |  | Pass
AT006 | Acceptance | Sample Output. Tried another destination with green truck with heavier weight | 500 1.0 8Y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y, 8Y | Fail | Program immediately crashed. Exception thrown. Error pointed at line 203, mapping.c
AT006.1 |  |  | 500 1.0 7Y |  | Pass | Map was displayed incorrectly. 8Y was a building that was not validated. To properly test GREEEN route changed destination to 7Y. Program is incorrectly validating 7Y to be a building.
AT007 | Acceptance | Sample Output. Test destination closest to blue Truck with diversion. | 500 1.0 8Y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y, 8Y | Fail | Program immediately crashed. Exception thrown. Error pointed at line 203, mapping.c
AT007.1 |  |  | 500 1.0 7Y |  | Pass | Map was displayed incorrectly. 8Y was a building that was not validated. To properly test GREEEN route changed destination to 7Y. Program is incorrectly validating 7Y to be a building.
AT008 | Acceptance | Sample Output. Exitting the program. | 0 0 x | Thanks for shipping with Seneca! | Fail | Output is correct. However has extra newlines. Before final print text.
AT008.1 |  |  |  |  | Pass
AT009 | Acceptance | Test yellow route validation. | 500 1.0 10B | Ship on yellow route, no diversion | Fail | Program is indicating that the yellow route is
AT010 | Acceptance | Testing building indicator | 500 1.0 7Y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y | Pass | Controll check to see capital letter are configured correctly
AT010.1 | Acceptance |  | 500 1.0 7y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y | Fail | y was not properly configured. Reading output for column was producing the ASCII value for "H"
AT010.2 | Acceptance |  | 500 1.0 7y |  | Pass
AT010.3 | Acceptance | Testing building indicator on coordinate where ASCII value is greater than 57 | 500 1.0 11L | Ship on BLUE LINE, no diversion | Pass
AT010.4 | Acceptance |  | 500 1.0 11l | Ship on BLUE LINE, no diversion | Fail | Output indicated a building is present when it was not.
AT010.5 | Acceptance | Testing building output check | 20 .5 12L | This is a building | Fail | Expected the program see value 1 on map, however causes a memory leak instead.
AT010.6 | Acceptance | Testing building within ASCII numbers | 20 .5 10B | Yellow Line no diversion | Fail | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"
AT010.7.1 | Acceptance | Fixed intended output.
AT010.7.2 | Acceptance | Testing building indicator | 500 1.0 7Y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y | Fail | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"
AT010.7.3 | Acceptance |  | 500 1.0 7y | Ship on GREEN LINE, divert: 7T, 7U, 7V, 7W, 7X, 7Y | Fail | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"
AT010.7.4 | Acceptance |  | 500 1.0 7y |  |  | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"
AT010.7.5 | Acceptance | Testing building indicator on coordinate where ASCII value is greater than 57 | 500 1.0 11L | Ship on BLUE LINE, no diversion | Fail | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"
AT010.7.6 |  |  | 500 1.0 11l | Ship on BLUE LINE, no diversion | Fail | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"
AT010.7.7 |  | Testing building output check | 20 .5 12L | This is a building | Fail | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"
AT010.7.8 |  | Testing building within ASCII numbers | 20 .5 10B | Yellow Line no diversion | Fail | Now indicating that this is a building. Checked output value for rows and column. Value is showing as "1"